## Sheet1
|  |  | July |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  | February |  | March |  |  |  | April |  |  |  | May |  |  |  | June
ID | Task Name | Duration (in Hrs) | W2 | w3 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Preliminary Meetings | bar: July W2 to July w3
1.1 | Project Topic Identification | bar: July w3
2 | Scope definition | bar: August W1 to August W3
3 | Drafting Proposal and Presentation | bar: August W3 to August W4
4 | Capture Requirements | bar: September W1 to September W3
4.1 | Project Start Up Meeting | bar: September W1 to September W2
4.2 | SRS documentation | bar: September W2 to September W3
5 | Analyze Requirments | bar: September W4 to October W4
5.1 | Data Requirement Analysis | bar: September W4 to October W1
5.2 | Entity Relationship Modeling | bar: October W1
5.3 | Form Modeling | bar: October W2
5.4 | Functional Lists | bar: October W3
5.6 | Protyping Software | bar: October W3 to October W4
6 | Design Solution | bar: November W1 to December W1
6.1 | Choosing Platform | bar: November W1
6.2 | Code Organization | bar: November W1
6.3 | Top-Level Design | bar: November W1 to November W3
6.4 | Low-level Design | bar: November W2 to November W3
6.5 | Module Testing | bar: November W4
6.6 | Objective Design Review | bar: December W1
7 | Develop Solution | bar: December W2 to March W2
7.1 | Set up the development Strategy | bar: December W2
7.2 | Establishing Programming Standards | bar: December W2
7.3 | Coding | bar: February W3 to March W2
8 | System Integration and Testing | bar: March W3 to April W2
8.1 | System Integration | bar: March W3 to March W4
8.2 | System Testing | bar: March W4
8.3 | Automated Testing | bar: March W4 to April W1
8.4 | Alpha Testing | bar: April W1 to April W2
8.5 | Beta Testing | bar: April W2 to April W3
9 | Acceptance and Deployment | bar: April W3 to May W1
10 | User Documentation | bar: May W2 to May W4