## Sheet1
|  |  | July |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
ID | Task Name | Duration (in Hrs) | W2 | w3 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W4 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Preliminary Meetings | bar: July W2 to July w3
1.1 | Project Topic Identification | bar: July w3
2 | Scope definition | bar: August W1 to August W3
3 | Drafting Proposal and Presentation | bar: August W3 to August W4
4 | Capture Requirements | bar: September W1 to September W3
4.1 | Project Start Up Meeting | bar: September W1 to September W2
4.2 | SRS documentation | bar: September W2 to September W3
5 | Analyze Requirments | bar: September W4 to October W4
5.1 | Data Requirement Analysis | bar: September W4 to October W1
5.2 | Entity Relationship Modeling | bar: October W1
5.3 | Form Modeling | bar: October W2
5.4 | Functional Lists | bar: October W3
5.6 | Protyping Software | bar: October W3 to October W4
6 | Design Solution | bar: November W1 to December W2
6.1 | Choosing Platform | bar: November W1
6.2 | Code Organization | bar: November W1
6.3 | Top-Level Design | bar: November W2 to November W3
6.4 | Low-level Design | bar: November W4 to December W1
6.5 | Module Testing | bar: December W2
6.6 | Objective Design Review
7 | Develop Solution
7.1 | Set up the development Strategy
7.2 | Establishing Programming Standards
7.3 | Coding
8 | System Integration and Testing
8.1 | System Integration
8.2 | System Testing
8.3 | Automated Testing
8.4 | Alpha Testing
8.5 | Beta Testing
9 | Acceptance and Deployment
10 | User Documentation